## Sheet1
Phase | Goal | Main Files | Test File | Estimated Days
Phase 1: Bootstrap Setup | Basic system structure with Docker and folders | .env, docker-compose.yml, Dockerfiles | test_bootstrap.py | 2
Phase 2: Simulator Engine | Generate state_json and write to DB | time_manager.py, weather_engine.py, occupant_engine.py, state_builder.py, simulator_main.py | test_simulator_tick.py | 5
Phase 3: CoreLogic Engine | Process tick: sensors, rules, MQTT actions | db_connector.py, sensor_manager.py, rule_engine.py, device_manager.py, mqtt_publisher.py, corelogic_main.py | test_corelogic_tick.py | 6
Phase 4: Sensor Modules | Implement all sensor classes with MQTT support | motion_sensor.py, temperature_sensor.py, gas_sensor.py, etc. | test_all_sensors.py | 4
Phase 5: Device Modules | Implement all device classes with MQTT actions | lights.py, air_conditioner.py, tv_living_room.py, etc. | test_all_devices.py | 4
Phase 6: WebUI | React dashboard to display latest processed tick | App.jsx, DashboardClient.js, RoomMap.jsx, etc. | test_webui_render.py | 5
Phase 7: Full Integration | Run full tick through all components and verify DB | N/A (system-wide) | test_full_integration.py | 3
Phase 8: Optional Features | Replay, WebSocket, animations, API improvements | To be determined | N/A | 5